## Risk-Oppty Register
Risk and Opportunity Register
| Date Created | 2024-05-21 | Created By: | Marcus Rosati
| Date Last Modified | 2024-05-21 | Modified By | Marcus Rosati
Risk Register
| Risk Element |  | Specific Action Required to Mitigate Risk | Approximate Severity of Risk if Fully Realized | Probability of Risk Realization | Detection Risk | Probability Adjusted Magnitude of Risk Estimate
| 1 | (Example) Accelerator sticks, forcing redesign | Redesign Accelerator | 10000000 | 0.5 | 0.9 | 4500000
| 2 | (Example) Accelerator sticks, forcing recall | In addition to redesign, must recall autos and retrofit part | 900000000 | 0.01 | 0.7 | 6300000
| 3 | (Example) Trends in quality defects are not reviewed in a way to identify problems early | Trend production data in SPC. Call in Black Belt to create custom reports to better utilize defect data. | 900000 | 0.7 | 1 | 630000
| 4 | (Example) Subcontractor machining process will limit chassis production once factory flow stabilizes. If a single machine goes down, it will jeopardize existing rate. | Implement Preventative Maintenance immediately. Create a replenishment fund and replacement schedule (~10yr window) | 3000000 | 0.25 | 0.7 | 525000
| 5 | (Example) Laser balancing equipment is aging, and has no backup |  | 3000000 | 0.13 | 0.7 | 273000
| 6 | (Example) Inadequate FOD Control results in lost manufacturing time, audits, and delays | Implement transition to world class FOD facility over the next year. | 750000 | 1 | 0.13 | 97500
| 7 | (Example) Quartz cleaning station is single threaded | Implement Preventative Maintenance immediately. Create a replenishment fund and replacement schedule (~10yr window) | 250000 | 0.2 | 0.5 | 25000
| 8 | (Example) Moisture problems in parts and PWBs causes latency | PWBs/CCAs and moisture sensitive parts stored in N2 | 125000 | 0.2 | 1 | 25000
| 9 | (Example) Single piece of equipment for particle removal station | Implement Preventative Maintenance immediately. Create a replenishment fund and replacement schedule (~10yr window) | 200000 | 0.2 | 0.5 | 20000
| 10 | (Example) PMs currently can override CCB, and configuration changes can cause delays and audit problems | Implement & fund CCB with authority to overrule PMs | 250000 | 0.2 | 0.25 | 12500
|  |  | Fully Realized Risk | 918475000 | Probability Adjusted |  | 12408000
Opportunity Register
| Opportunity Element |  | Specific Action Required to Harvest Opportunity | Approximate Benefit if Fully Realized | Probability of Oppty Realization | Detect-ability | Probability Adjusted Magnitude of Oppty Estimate
| 1 | (Example) New Accelerator Improves Response - Increases Sales | Redesign Accelerator, with emphasis on acceleration response | 240000000 | 0.04 | 0.9 | 8640000
| 2 | (Example) Reduce accelerator part count | Move from 3 parts to two parts, saving 10% | 900000000 | 0.01 | 0.7 | 6300000
| 3 | (Example) Piggyback recall with other scheduled maintenance | Look at opportunity to couple fix with PM, saves 50% of recall cost (See risk 2 x .5) | 3150000 | 0.5 | 1 | 1575000
| 4 | (Example) Subcontractor machining process improvement increases throughput | Improved productivity ~5% | 300000 | 0.25 | 1 | 75000
| 5 | (Example) Laser cutter more effective, lowers scrap rate by 5% | %5 improvement in scrap = $2M increase in profit | 2000000 | 0.1 | 1 | 200000
| 6 | [5 empty] | 0
| 7 | [5 empty] | 0
| 8 | [5 empty] | 0
| 9 | [5 empty] | 0
| 10 | [5 empty] | 0
|  |  | Fully Realized Opportunity | 1145450000 | Probability Adjusted |  | 16790000
Note on B6: Place a unique alphanumeric here to identify the risk
Note on B24: Place a unique alphanumeric here to identify the oppty
Note on C6: A good, but short description of the risk - if you need to describe in more detail, refer to an appendix and add there.
Note on C24: A good, but short description of the oppty - if you need to describe in more detail, refer to an appendix and add there.
Note on D6: A short description of what you need to do to mitigate this risk - if you need to describe in more detail, refer to an appendix and add there.
Note on D24: A short description of what you need to do to realize this oppty - if you need to describe in more detail, refer to an appendix and add there.
Note on E6: If the risk event happened, what would the financial impact be? Add any supporting calcs to the appendix
Note on E24: If the oppty were fully realized, what would the financial impact be? Add any supporting calcs to the appendix
Note on F6: What are the chances that this risk will occur if no action is taken? 0 = none 1 = 100% likely
Note on F24: What are the chances that this oppty will happen if action is taken? 0 = none 1 = 100% likely
Note on G6: If the risk were to happen, what are the chances we would miss it before it was realized? 0 = would always detect and mitigate before risk happened 1= there is no way we sould know before it was too late?
Note on G24: If the oppty were realized, what are the chances we would be able to tell (financially)? 0 = We would not be able to tell 1=We would always know
Note on H6: Adjusted Risk = Severity x probabiliity x detection
Note on H24: Adjusted Oppty = Severity x probabiliity x detection

## Appendix
Appendix - Risk and Opportunity Register
Unique Identifier | Risk or Oppty | Basis for assumption | Who will be affected by the risk (e.g., who would bear the cost if the risk did occur) | The timeframe during which the risk is likely to occur (e.g., "during the design phase") | What is being done to prevent this risk from occurring (usually a textual description) | What actions must be undertaken if the risk does occur (usually a textual description) | Who will be affected by the risk (e.g., who would bear the cost if the risk did occur) | The timeframe during which the risk is likely to occur (e.g., "during the design phase") | What is being done to prevent this risk from occurring (usually a textual description) | What actions must be undertaken if the risk does occur (usually a textual description)